## Gantt Chart w % Complete
Build better gantt charts with TeamGantt for FREE!
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | PERCENT COMPLETE | WEEK 1 / WEEK 5 | WEEK 2 / WEEK 6 | WEEK 3 / WEEK 7 | WEEK 4 / WEEK 8
Review 0
| Topic Finalization | 2021-02-07 | 7 | 2021-02-11 | 5 | 5 | 0 | 100%
| Group allocation | 2021-02-11 | 11 | 2021-02-13 | 3 | 3 | 0 | 100%
| Preparing presentation | 2021-02-13 | 13 | 2021-02-18 | 6 | 6 | 0 | 100%
Review 1
| Literature Review | 2021-02-16 | 16 | 2021-03-10 | 23 | 23 | 0 | 100%
| Contacting Industry person | 2021-03-19 | 19 | 2021-03-20 | 2 | 2 | 0 | 100%
| Aquiring testing information | 2021-03-20 | 20 | 2021-03-22 | 3 | 3 | 0 | 100%
| Planning for Review 1 | 2021-03-20 | 20 | 2021-04-07 | 19 | 19 | 0 | 100%
Review 2
| Collecting Data | 2021-04-07 | 7 | 2021-05-07 | 31 | 31 | 0 | 100%
| Sorting Data | 2021-05-08 | 8 | 2021-05-09 | 2 | 2 | 0 | 100%
| Plotting Xbar and R charts | 2021-05-09 | 9 | 2021-05-10 | 2 | 2 | 0 | 100%
| Check Sheet and Pareto Chart | 2021-05-10 | 10 | 2021-05-13 | 4 | 4 | 0 | 100%
| Preparing presentation | 2021-05-10 | 10 | 2021-05-21 | 12 | 12 | 0 | 100%
Review 3
| Np Chart | 2021-05-15 | 15 | 2021-05-16 | 2 | 2 | 0 | 100%
| Cause and Effect Diagram | 2021-05-17 | 17 | 2021-05-20 | 4 | 4 | 0 | 100%
| CUSUM chart | 2021-05-22 | 22 | 2021-05-23 | 2 | 2 | 0 | 100%
| Cost calculation | 2021-05-24 | 24 | 2021-05-26 | 3 | 3 | 0 | 100%
| Preparing presentation | 2021-05-22 | 22 | 2021-05-28 | 7 | 7 | 0 | 100%
| Report | 2021-05-17 | 17 | 2021-06-08 | 23 | 23 | 0 | 100%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1